## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Identify metrics & review. | Day 0: 5; Day 1: 1; Day 5: 2
2 | Design pattern identification & review. | 5 | 1 |  | 1 | 1 | 1
3 | Pinpoint code smells & review. | 5 | 1 |  | 1 | 1 | 1.5
4 | Compile reports (Metrics, GoF, Smells) & review. | Day 0: 5; Day 1: 1; Day 5: 4
5 | Make Use Case diagram & review | Day 0: 5; Day 1: 1; Day 5: 2
6
7
8
9
10
Completed Effort |  | 0 | 5 | 0 | 2 | 2 | 9 | 0 | 0
Remaining Effort |  | 25 | 20 | 20 | 18 | 16 | 7 | 7 | 7
Ideal Burndown |  | 25 | 23.3333 | 21.6667 | 20 | 18.3333 | 16.6667 | 15 | 13.3333