## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-29 | 2023-11-30 | 2023-12-01
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Setup the Forked FreeCol repository. | 1 | 1
2 | Study the existing source code. | 4 | 2 | 2
3 | Discuss a new use case | 2 | 2
4 | Implement funcionalities | 4 | 1
Completed Effort |  | 0 | 6 | 2 | 0
Remaining Effort |  | 11 | 5 | 3 | 3
Ideal Burndown |  | 11 | 10.2667 | 9.5333 | 8.8